## Task WBS
RMF ATO Tasks - Design | Part(ies) Responsible | Estimated Hours | Unit Rate | Estimated Total Cost
Step 1 Categorize System
EI&E Control Systems Master List | System Integrator, System Owner, Authorizing Official | 2 | 200 | 400
Step 2 Select Security Controls
EI&E NIST SP 800-82 R2 FRCS Overlay (excel file) | System Integrator, System Owner | 4 | 200 | 800
Step 3 Implement Security Controls
Draft 35% Design RMF Security Core Authorization Package (excel file) | System Integrator | 100 | 200 | 20000
Draft 100% Design RMF Security Core Authorization Package (excel file) | System Integrator | 20 | 200 | 4000
Draft 35% Design all RMF docs and artifacts (SSP, SAR, POAM, ITCP, EICP, SIRP, etc.) | System Integrator and Vendor Subs | 100 | 200 | 20000
Draft Design 100% all RMF docs and artifacts (SSP, SAR, POAM, ITCP, EICP, SIRP, etc.) | System Integrator and Vendor Subs | 20 | 200 | 4000
Step 4 Assess Security Controls |  |  |  | 0
Core Preliminary Security Assessment Report (Project generated) | System Integrator | 20 | 200 | 4000
Step 5 Authorize System |  |  |  | 0
Draft Authorization Decision Document | System Owner, Authoring Official | 2 | 200 | 400
|  | 268 |  | 53600
RMF ATO Tasks - Construction
Create Test and Development Environment (VM, Components, SCAP/STIG) | System Integrator | 40 | 200 | 8000
Create Jump-Kit Rescue CD / DVD (and update as required) | System Integrator | 80 | 200 | 16000
Conduct FAT and SAT Testing | System Integrator | 100 | 200 | 20000
Step 4 Assess Security Controls |  |  |  | 0
Core Preliminary Security Assessment Report (Project generated excel) | System Integrator | 20 | 200 | 4000
Core Preliminary Plan of Action and Milestones (Project generated excel) | System Integrator | 20 | 200 | 4000
Assist to upload into eMASS the excel Core SSP data | System Integrator | 15 | 200 | 3000
eMASS generated Security Assessment Report (SAR) - Security Controls Assessor | System Owner | 0 |  | 0
eMASS generated Plan Of Action Milestones (POAM) | System Owner | 0 |  | 0
Resolve SCA Findings | System Integrator and Vendor Subs | 80 | 200 | 16000
Step 5 Authorize System |  |  |  | 0
Authorization Decision Document | System Owner, Authoring Official | 2 | 200 | 400
|  | 357 |  | 71400
Other Technical Support | Total | 625 |  | 125000
Step 6 Monitor Security Controls |  |  |  | 0
Monthly Security Audit (SysAdmin, 3rd Party Auditor, FM - 8 hours per month each) | System Integrator, System Owner | 24 | 200 | 4800
Annual Review of 1/3 Security Controls | System Integrator, System Owner | 80 | 200 | 16000
Patch Management/Daily Operations | System Integrator, System Owner | 160 | 200 | 32000
Perform Penetration Testing (if required) | System Integrator, System Owner | 40 | 200 | 8000
Manage TDE (Monthly SCAP/STIG scans, Patches, Vulnerability Management (8 hours per month) | System Integrator, System Owner | 8 | 200 | 1600